## Project Overview
Healthcare Claims Voice Assistant
Section 1: Project Details |  | Section 2: Project Snapshot
Organization | EXL Services | Total Modules | 8
Domain | Healthcare | Total APIs | 4
Project Type | AI-Powered Voice Assistant | Test Categories | 6
Objective | 1. Simplify healthcare assistance 2. Enable secure member verification 3. Provide real-time claim information 4. Improve service accessibility 5. Deliver fast voice responses | Total Test Cases
Edge Cases
|  | Overall Status | Completed
Deployment | Voice Agent + Static UI
Technology Stack | Google CX Agent Studio Google Cloud Functions REST APIs Static Web UI
Current Status | Successfully Completed & Tested
Github Repository
Team | Ramaz Rhythm Palak Manhas Pragati Neha

## Project Modules
Project Modules
Section 1: Module Progress |  |  |  | Section 2: Integration Status |  | Section 3: Project Progress
Module ID | Project Module | Purpose | Status | Component | Integrated | Category | Completion
M-01 | User Authentication | Member Verification | Completed | Google Cloud CX | Yes | Requirements | 100%
M-02 | Claim Status | Claim Information | Completed | Cloud Functions | Yes | Development | 100%
M-03 | Eligibility Check | Coverage Verification | Completed | Claims API | Yes | API integration | 100%
M-04 | Benefits Information | Benefits Lookup | Completed | Eligibility API | Yes | Voice Flow | 100%
M-05 | Provider Search | Provider Lookup | Completed | Benefits API | Yes | Testing | 100%
M-06 | Human Escalation | Live Agent Transfer | Completed | Provider API | Yes | Documentation | 100%
M-07 | Voice Integration | Conversational Flow | Completed | Static UI | Yes | Deployment | 100%
M-08 | Static Web UI | User Interface | Completed | Github Repository | Yes

## Test Case Summary
Test Case Summary
Test Category | Total Cases | Passed | Failed | Pass Rate | Detailed Sheet
Functional |  |  |  |  | Functional Test Cases
Golden |  |  |  |  | Golden Test Cases
Negative |  |  |  |  | Negative Test Cases
Edge |  |  |  |  | Edge Test Cases
Escalation |  |  |  |  | Escalation Test Cases
Security |  |  |  |  | Security & Guardrails
Tool & API |  |  |  |  | Tool & API Validation
Overall Testing Metrics
Metric | Value
Total Test Cases
Executed
Passed
Failed
Pass Rate
Overall Result | Successful
Sec 1: Test Execution Summary
Metric | Value
Total Test Cases
Executed
Passed
Failed
Pass Rate
Overall Result | Successful

## Functional Test Cases
Test Case Register: Functional Test Cases
Section 1: Root Agent and Conversation Management
TC ID | Journey | Scenario | Test Type | Priority | Expected Result | Semantic Similarity (4) | Tool Correctness | Hallucination | Actual Result | Status
F-001 | Root Agent | Handle Out-of-Scope Request | Negative | High | Appropriate fallback response provided | 4 | 100% | No | Fallback response returned | Pass
F-002 | Root Agent | Escalate after 3 consecutive Unclear Requests | Escalation | High | Conversation transferred to human agent | 4 | 100% | No | Escalated successfully | Pass
F-003 | Root Agent | Transfer to Human Representative on Request | Positive | High | User transferred immediately | 4 | - | No | Transfer successful | Pass
F-004 | Root Agent | Root Agent Identifies Claim Status Intent | Positive | High | User routed to Claims Journey Agent | 4 | 100% | No | Routed successfully | Pass
Section 2: Consent Management
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-005 | Consent | Consent Granted | Positive | High | Authentication starts | 4 | 100% | No | Routed successfully | Pass
F-006 | Consent | Consent Declined | Negative | High | Conversation ends successfully | 4 | 100% | No | Session ended | Pass
F-007 | Consent | Grant consent after initially declining | Edge Case | Medium | User proceeds after granting consent later | 4 | 100% | No | Flow resumed | Pass
Section 3: Authentication and Identity Verification
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-008 | Authentication | Valid member ID | Positive | High | Valid Member ID accepted | 4 | 100% | No | Authentication started | Pass
F-009 | Authentication | Invalid Member ID | Negative | High | Retry prompt returned | 4 | 100% | No | Prompt returned | Pass
F-010 | Authentication | Accept Valid Member ID after Invalid | Edge Case | High | Authentication continues | 4 | 100% | No | Authentication resumed | Pass
F-011 | Authentication | Different DOB formats | Edge Case | Medium | Supported DOB formats accepted | 4 | 100% | No | DOB validated | Pass
F-012 | Authentication | DOB in MM/DD/YYYY format | Positive | Medium | DOB validated | 4 | 100% | No | DOB accepted | Pass
F-013 | Authentication | User asks an Invalid Question | Edge Case | Medium | Authentication Flow maintained | 4 | 100% | No | Flow continued | Pass
F-014 | Authentication | Handles Credentials Refusal | Negative | High | Graceful refusal handling | 4 | 100% | No | Conversation handled correctly | Pass
F-015 | Authentication | Incorrect Verification Credential | Negative | High | Authentication denied | 4 | 100% | No | Access denied | Pass
F-016 | Authentication | Re-entering Correct Credentials | Edge Case | High | Authentication successful | 4 | 100% | No | Authentication completed | Pass
F-017 | Authentication | Agent doesnot reveal information before authenticated | Security | Critical | No PHI exposed before verification | 4 | 100% | No | Information protected | Pass
F-018 | Authentication | 3 failed authentication attempts | Escalation | Critical | Human escalation triggered | 4 | 100% | No | Escalated | Pass
F-019 | Authentication | 3 failed Invalid Member ID attempts | Escalation | Critical | Human escalation triggered | 4 | 100% | No | Escalated | Pass
Section 4: Claims Journey
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-020 | Claims Journey | Displays Claim History | Positive | High | Claim History provided | 4 | 100% | No | History retrieved | Pass
F-021 | Claims Journey | Submits New Claim | Positive | Medium | Claim submission assistance provided | 4 | 100% | No | Request handled | Pass
F-022 | Claims Journey | Handles Claim Cancellation Request | Negative | Medium | appropriate cancellation response provided | 4 | 100% | No | Cancellation handled | Pass
Section 5: Eligibility & Benefits
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-023 | Eligibility | Retrieves Eligibility information | Positive | High | Eligibility details provided | 4 | 100% | No | Eligibility retrieved | Pass
F-024 | Eligibility | Handles No Eligibility Record Found | Negative | Medium | Appropriate message provided | 4 | 100% | No | Message given | Pass
F-025 | Benefits | Retrieves Benefits Infrmation | Positive | High | Benefits provided | 4 | 100% | No | Benefits retrieved | Pass
F-026 | Benefits | Handles No Benefits Information Found | Negative | Medium | Appropriate message provided | 4 | 100% | No | Message given | Pass
Section 6: Provider Lookup & Preauthorization
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-027 (I) | Provider Lookup | Retrieves Assigned Provider | Positive | High | Assigned provider provided | 3.7 | 100% | No |  | Fail
F-027 (II) | Provider Lookup | Retrieves Assigned Provider | Positive | High | Assigned provider provided | 4 | 100% | No | Provider retrieved | Pass
F-028 (I) | Provider Lookup | Provider Search by City | Positive | Medium | Providers listed by city | 4 | 100% | Yes |  | Fail
F-028 (II) | Provider Lookup | Provider Search by City | Positive | Medium | Providers listed by city | 4 | 100% | No | Providers retrieved | Pass
F-029 | Provider Lookup | Provider Search by ZIP Code | Positive | Medium | Providers listed by ZIP | 3.7 | 100% | No | Providers retrieved | Pass
F-030 (I) | Provider Lookup | Provider Search by Provider Name | Positive | Medium | Provider found | 3.9 | 100% | Yes |  | Fail
F-030 (II) | Provider Lookup | Provider Search by Provider Name | Positive | Medium | Provider found | 3.9 | 100% | No | Provider retrieved | Pass
F-031 | Preauthorization | Verify Preauthorization Status Retrieval | Positive | High | Current status given | 4 | 100% | No | Status shared | Pass
Section 7: Cross-Agent Routing & Security
TC ID | Journey | Scenario | Test Type | Priority | Expected Result |  |  |  | Actual Result | Status
F-032 | Agent Routing | Claims Requests transfer from provider & preauthorization agent to Claims agent | Positive | High | Request routed to Claims Journey Agent | 3.9 | 100% | No | Routing successful | Pass
F-033 | Security | Provider & Preauthorization Agent refuses to share internal system details | Security | Critical | Internal System Information is protected | 4 | 100% | No | Information not disclosed | Pass

## Golden Test Cases
Test Case Register: Golden (Happy Path) Test Cases
TC ID | Journey | Scenario | Test Type | Priority | Expected Result | Semantic Similarity (4) | Tool Correctness | Hallucination | Actual Result | Status
G-01 | Intent Recognition | Wrong Intent Handling | Positive | Medium | Voice assistant identifies the unsupported intent and responds appropriately without breaking conversation flow | 4 | 100% | No | Unsupported intent handled correctly | Pass
G-02 | Consent Management | No Consent | Negative | Medium | Voice assistant respects user's decision and securely terminates the conversation without accessing PHI | 4 | 100% | No | Conversation ended securely after consent was declined | Pass
G-03 (I) | Claim Journey | Claims Status Journey | Positive | Critical | Voice assistant authenticates the member and provides the current claim status | 4 | 80% | No |  | Fail
G-03 (II) | Claim Journey | Claims Status Journey | Positive | Critical | Voice assistant authenticates the member and provides the current claim status | 3.9 | 100% | No | Claim status successfully provided | Pass
G-04 (I) | Eligibility Journey | Eligibility Check Journey | Positive | High | Voice assistant verifies member eligibility and provides eligibility information | 4 | !00% | Yes |  | Fail
G-04 (II) | Eligibility Journey | Eligibility Check Journey | Positive | High | Voice assistant verifies member eligibility and provides eligibility information | 4 | 100% | No | Eligibility successfully verified | Pass
G-05 (I) | Benefits Journey | Benefits Journey | Positive | High | Voice assistant retrieves and communicates the member's benefit information accurately | 3.6 | 100% | No |  | Fail
G-05 (II) | Benefits Journey | Benefits Journey | Positive | High | Voice assistant retrieves and communicates the member's benefit information accurately
G-06 | Provider Lookup journey | Provider Lookup Journey | Positive | High | Voice assistant retrieves the assigned provider details successfully | 4 | 100% | No | Assigned provider information retrieved | Pass
G-07 (I) | Preauthorization Journey | Preauthorization Status Journey | Positive | High | Voice assistant retrieves the current preauthorization status successfully | 4 | 96% | No |  | Fail
G-07 (II) | Preauthorization Journey | Preauthorization Status Journey | Positive | High | Voice assistant retrieves the current preauthorization status successfully | 4 | 100% | No | Preauthorization status retrieved | Pass

## Negative Test Cases
Test Case Register: Negative Test Cases
TC ID | Journey | Scenario | Test Type | Priority | Expected Result | Semantic Similarity (4) | Tool Correctness | Hallucination | Actual Result | Status
N-01 | Authentication | Invalid Member ID | Negative | High | Rejects invalid Mem ID and prompts user to provide valid Mem ID | 4 | 100% | No | invalid Member ID rejected and retry requested | Pass
N-02 (I) | Authentication | Invalid DOB | Negative | High | Rejects invalid DOB and asks user to provide the correct DOB | 4 | 100% | No | Invalid DOB rejected and retry requested | Pass
N-02 (II) | Authentication | Invalid ZIP Code | Negative | High | Rejects invalid ZIP code and prompts the user to provide a valid ZIP code | 4 | 100% | Yes |  | Fail
N-03 | Authentication | Invalid ZIP Code | Negative | High | Rejects invalid ZIP code and prompts the user to provide a valid ZIP code | 4 | 100% | No | Invalid ZIp code rejjected and retry requested | Pass
N-04 (I) | Authentication | Invalid Last $ Digits of SSN | Negative | High | Rejects incorrect verification credentials and requests valid information | 4 | 100% | No | Invalid SSN rejected and authentication not completed | Pass
N-04 (II) | Authentication | Invalid Member ID (3 attempts) | Escalation | Critical | Stops further authentication attempts and transfers the interaction for manual assistance | 4 | 93% | No |  | Fail
N-05 | Authentication | Invalid Member ID (3 attempts) | Escalation | Critical | Stops further authentication attempts and transfers the interaction for manual assistance |  |  |  | Conversation escalated after three invalid Mem IDs | Pass
N-06 | Authentication | Consecutive Authentication Failures | Escalation | Critical | Escalates the interaction after repeated authentication failures | 4 | 100% | No | Conversation escalated successfully | Pass
N-07 (I) | Provider Search | Invalid Provider Name | Negative | Medium | Informs the user that no matching provider was found and asks for another search value | 4 | 100% | No | No provider found; user prompted to refine the user | Pass
N-07 (II) | Provider Search (I) | Invalid City | Negative | Medium | Indicates that no providers were found for the specified city and requests another location | 3.8 | 100% | Yes |  | Fail
N-08 | Provider Search (II) | Invalid City | Negative | Medium | Indicates that no providers were found for the specified city and requests another location | 4 | 100% | No | No providers found for the city | Pass
N-09 | Provider Search | Invalid ZIP for Provider Search | Negative | Medium | Informs no providers were found for the specified ZIP code and requests another ZIP code of search criterion | 3.8 | 100% | No | User prompted to enter a valid ZIP code | Pass
N-10 | Benefits | Benefits Request for Member without Benefits Record | Negative | High | Informs the user that no benefits information is available for the authenticated member without exposing sensitive information | 4 | 100% | No | No benefits record found, appropriate response returned | Pass

## Edge Case Test Cases
Test Case Register: Edge Cases and Error Handling
Section 1: Authentication
TC ID | Journey | Scenario | Test Type | Priority | Expected Result | Semantic Similarity (4) | Tool Correctness | Hallucination | Actual Result | Status
ED-01 | Authentication | User changes intent before giving consent | Edge Case | Medium | Voice assistant identifies the new intent and responds appropriately while maintaining the conversation errors. |  |  |  | Intent changes successfully | Pass
ED-02 | Authentication | User repeats the same credential multiple times | Edge Case | Medium | Voice assistant recognizes the repeated input without causing conversation errors |  |  |  | Repeated credential handled successfully | Pass
ED-03 | Authentication | User repeats more time before responding | Edge Case | Low | Voice assistant waits or reprompts without causing conversation errors |  |  |  | Additional time provided | Pass
ED-04 | Authentication | User provides extra unrelated information during authentication | Edge Case | Medium | Voice assistant ignores unrelated information and continues authentication |  |  |  | Extra information handled successfully | Pass
ED-05 | Authentication | User provide mulitple authentication credentials in a single utterance | Edge Case | High | Voice assistant extracts all credentials correctly and proceed with authentication |  |  |  | Multiple credentials processed successfully | Pass
ED-06 | Authentication | User answers before the prompt completes | Edge Case | Medium | Voice assistant captures the interruption and continues the conversation correctly |  |  |  | Early response processed successfully | Pass
ED-07 | Authentication | User asks why authentication information is required | Edge Case | Low | Voice assistant explains the purpose of authentication and resumes the process |  |  |  | Explanation provided and authentication continued | Pass
ED-08 | Authentication | User asks to repeat the previous question | Edge Case | Low | Voice assistant repeats the previous prompt accurately |  |  |  | Previous prompt repeated | Pass
ED-09 | Authentication | User corrects a previously provided credential | Edge Case | Medium | Voice assistant updates the credential and continues authentication |  |  |  | Updated credential accepted | Pass
Section 2: Root Agent
ED-10 | Root Agent | User makes multiple supprted requests in a single utterance | Edge Case | High | Voice assistant identifies all supported requests and processes them correctly |  |  |  | Multiple supported requests handled successfully | Pass
ED-11 | Root Agent | User combines a supported and unsupported request | Edge Case | High | Voice assistant processes the supported request and handles the unsupported request appropriately |  |  |  | Mixed requests handled successfully | Pass
ED-12 | Root Agent | User greets and requests a service in the same utterance | Edge Case | High | Voice assistant acknowledges the greeting and continues with the requested service |  |  |  | Greeting and request processed successfully | Pass
Section 3: Claims Journey Agent
ED-13 | Claims Journey | User changes the requested claim service during the conversation | Edge Case | Medium | Voice assistant switches to the newly requested claim service without restarting the session |  |  |  | Claim service changed successfully | Pass
ED-14 | Claims Journey | User requests another healthcare service after completing the first request | Edge Case | Medium | Voice assistant transitions smoothly to the new service after completing the previous one |  |  |  | New service initiated successfully | Pass
ED-15 | Claims Journey | User repeatedly requests claim cancellation | Edge Case | High | Voice assistant handles repeated cancellation requests consistently without unexpected behavior |  |  |  | Repeated cancellation handled successfully | Pass
Section 4: Provider and Preauthorization
ED-16 | Provider & Preauthorization | User changes search criteria during provider lookup | Edge Case | Medium | Voice assistant updates the search criteria and returns results based on the latest input |  |  |  | Search criteria updated successfully | Pass
Section 5: Cross-journey Navigation
ED-17 | Conversation Flow | User makes a new supported request immediately after authentication | Edge Case | Medium | Voice assistant recognizes the new request and routes the user to the appropriate journey without requiring re-authentication |  |  |  | New Journey initiated successfully | Pass

## KPI Dashboard
AI Performance KPI Dashboard
Section 1: Conversational AI KPIs
KPI ID | KPI Name | Target | Actual | Status
KPI-001 | Intent Recognition Accuracy | >95%
KPI-002 | Task Completion Rate | >95%
KPI-003 | Fallback Rate | <10%
KPI-004 | Containment Rate | >90%
KPI-005 | Human Escalation Rate | <10%
Section 2: Authentication & Security KPIs
KPI-006 | Authentication Success Rate | >95%
KPI-007 | Authentication Failure Rate | <5%
KPI-008 | Member Validation Accuracy | 100%
Section 3: API Performance KPIs
KPI -009 | API Success Rate | >98%
KPI -010 | Average Response Time | <2 sec
KPI -011 | API Error Rate | <2%
KPI -012 | Webhook Success Rate | >98%
Section 4: User Experience KPIs
KPI-013 | Average Conversation Turns | 8 to 15
KPI-014 | User Satisfaction Score | >4/5
KPI-015 | Overall Evaluation Score | >90%